## Method
DroneAid — Wideband Delphi Backlog Estimation
Estimation scale: modified Fibonacci story points (1, 2, 3, 5, 8, 13).
One story point ≈ 0.25 person-days of focused work.
Process applied:
1. Backlog items derived from the design spec acceptance criteria.
2. Five estimators (Aok, Belle, Bew, Poom, Tawan) independently estimate each item without seeing others' values.
3. Round 1: open submissions. Coordinator (Aok) computes spread (min / median / max / range).
4. Items with range > 2 Fibonacci steps go to discussion.
5. Round 2: estimators re-submit after hearing rationale for outliers.
6. Round 3: final convergence pass.
7. Consensus = median of Round 3 values, rounded to nearest Fibonacci step.
Convergence is visible in the Backlog sheet: spread column shrinks across R1 → R2 → R3.
Story points roll up by epic (Summary sheet) and by owner for capacity planning.
Estimator key:
E1 = Aok (Lead, Backend)
E2 = Belle (Identity + Shared UI)
E3 = Bew (Request Domain)
E4 = Poom (Tracking + Maps)
E5 = Tawan (Fleet Domain)

## Backlog
ID | Epic | User Story / Task | Acceptance Criteria | Owner | Priority | Sprint | Round 1 — E1..E5 |  |  |  |  | R1 Min | R1 Median | R1 Max | R1 Range | Round 2 — E1..E5 |  |  |  |  | R2 Min | R2 Median | R2 Max | R2 Range | Round 3 — E1..E5 |  |  |  |  | R3 Min | R3 Median | R3 Max | R3 Range | Consensus (SP) | Notes
[7 empty] | Aok | Belle | Bew | Poom | Tawan | Min | Median | Max | Range | Aok | Belle | Bew | Poom | Tawan | Min | Median | Max | Range | Aok | Belle | Bew | Poom | Tawan | Min | Median | Max | Range
US-01 | Identity | Register with Thai national ID + password | Form validates 13-digit ID + checksum; creates Firebase Auth user with synthetic email; users doc auto-provisioned with role=user. | Belle | Must | 1 | 5 | 3 | 5 | 5 | 8 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-02 | Identity | Login + logout | User logs in with ID + password; logout removes FCM token from users doc. | Belle | Must | 1 | 2 | 3 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-03 | Identity | Profile + Settings | User edits name, phone, delivery pin, language preference; data persisted to users doc. | Belle | Should | 2 | 3 | 5 | 3 | 3 | 5 |  |  |  |  | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-04 | Identity | Thai ID validator + unit tests | Pure-Dart + TS implementations sharing tests; rejects bad checksums. | Belle | Must | 1 | 2 | 3 | 2 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-05 | Catalog | Catalog browse + cart | User filters active+in-stock items, adds to cart with quantity, sees running weight total. | Bew | Must | 1 | 3 | 5 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 5 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-06 | Catalog | Delivery pin picker on map | User drops/edits a GPS pin; defaults to profile address. | Bew | Must | 1 | 3 | 2 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-07 | Request | Submit request | Calls submitRequest callable; client+server validate weight ≤ max payload and stock available. | Bew | Must | 1 | 3 | 5 | 3 | 3 | 5 |  |  |  |  | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-08 | Request | Queue page (live status) | Streams requests where userId == me; shows status chip + ETA when in flight. | Bew | Must | 1 | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-09 | Request | History page | Lists completed / failed / cancelled requests, newest first, with timestamp. | Bew | Should | 2 | 2 | 2 | 2 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-10 | Request | Admin Requests list with filters | Admin sees all requests; filters by status + priority; live updates. | Bew | Must | 1 | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-11 | Request | Admin Request Manage: approve/reject + drone picker | Admin views user profile + items; approves (stock decrement) or rejects with reason; drone picker filtered by payload + range. | Bew | Must | 1 | 8 | 5 | 5 | 5 | 8 |  |  |  |  | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-12 | Catalog | Admin Inventory + restock | Admin sees per-item stock; restocks via callable; deactivates items. | Bew | Should | 2 | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-13 | Fleet | Admin Drone list | All drones incl. offline + maintenance; status chip + battery bar. | Tawan | Must | 1 | 3 | 2 | 3 | 3 | 2 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-14 | Fleet | Admin Drone detail + future queue | Drone status, battery, current flight, planned future flights, maintenance toggle. | Tawan | Must | 1 | 5 | 5 | 8 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-15 | Fleet | Admin Weather panel | Admin sets global weather to clear/wind/storm via callable; setting drives sim. | Tawan | Must | 1 | 2 | 3 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-16 | Tracking | Tracking page with live map + interpolation | flutter_map renders origin/dest/drone marker; position computed client-side every frame from flight plan. | Poom | Must | 1 | 8 | 13 | 8 | 8 | 13 |  |  |  |  | 8 | 8 | 8 | 13 | 8 |  |  |  |  | 8 | 8 | 8 | 8 | 8
US-17 | Tracking | Confirm page + confirmDelivery wiring | Banner shown when status=delivered; tap calls callable; UI updates immediately. | Poom | Must | 1 | 2 | 3 | 2 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-18 | Tracking | Notifications inbox + FCM device registration | FCM token registered to users doc; inbox shows historic events from subcollection; tap-through navigates. | Poom | Must | 1 | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-19 | Tracking | Admin Control map (all active drones) | Map of every flying drone; tap a marker to see flight + request info. | Poom | Must | 1 | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-20 | Backend | Firebase project setup + emulator suite | Project created, Flutter + Functions wired, emulator runs Auth/Firestore/Functions locally. | Aok | Must | 1 | 3 | 5 | 3 | 3 | 5 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-21 | Backend | Firestore rules + indexes + rules unit tests | All collections have rules per spec §9; rules unit tests cover owner/admin/deny paths. | Aok | Must | 1 | 5 | 8 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-22 | Backend | onUserCreated trigger | Auth trigger writes users/{uid} with role=user, blank fcmTokens, defaults. | Aok | Must | 1 | 1 | 2 | 1 | 2 | 1 |  |  |  |  | 1 | 1 | 1 | 2 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1
US-23 | Backend | submitRequest callable | Validates payload, weight, stock; creates requests doc; returns reqId; FCM-notifies admins. | Aok | Must | 1 | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-24 | Backend | approveRequest + rejectRequest callables | approveRequest does tx: stock decrement + status change + return eligible drones. rejectRequest stores reason. | Aok | Must | 1 | 5 | 5 | 5 | 3 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-25 | Backend | assignDrone + cancelRequest callables | assignDrone creates flight, mutates drone + request statuses in tx. cancelRequest only when pending. | Aok | Must | 1 | 5 | 3 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-26 | Backend | tickFlights v0 (movement + transitions) | Scheduled every 60s; advances enroute→delivering→completed→returning→idle. | Aok | Must | 1 | 8 | 8 | 5 | 8 | 8 |  |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  |  |  | 8 | 8 | 8 | 8 | 8
US-27 | Backend | tickFlights failure dice (weather, battery, mech) | Adds storm 20%, battery <15%, mechanical 1% per tick; transitions to aborted/failed with type. | Aok | Must | 1 | 5 | 5 | 5 | 5 | 8 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-28 | Backend | confirmDelivery callable | Marks request confirmed; transitions drone to returning; FCM notification. | Aok | Must | 1 | 2 | 3 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-29 | Backend | setWeather + restockItem + toggleDroneMaintenance callables | Three admin-only callables for shared state changes. | Aok | Must | 1 | 3 | 2 | 3 | 3 | 2 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-30 | Backend | onFlightWritten trigger + FCM fan-out | Firestore trigger detects state transitions; sends FCM to user + admins as appropriate. | Aok | Must | 1 | 3 | 5 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 5 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-31 | Backend | Seed scripts (catalog, drones, admins, demo users) | Idempotent npm scripts populate Firestore for demo. | Aok | Must | 1 | 2 | 3 | 2 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-32 | DevOps | GitHub Actions CI (flutter + functions + rules + gitleaks + log-presence) | ci.yml runs on every PR + push to main; all gates green required to merge. | Aok | Must | 1 | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
US-33 | DevOps | Deploy workflows (functions + rules) | On push to main, deploys functions + rules using FIREBASE_SERVICE_ACCOUNT secret. | Aok | Must | 1 | 2 | 3 | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 2 | 2 | 2 | 2 | 2
US-34 | Audit | SessionEnd hook + copy + redact scripts | Each dev's session JSONL copied to docs/agent-logs/<handle>/ on session end, redacted of secrets. | Belle | Must | 1 | 3 | 5 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-35 | Audit | Log-presence + build-log-index workflows | log-presence fails PRs missing same-day log; build-log-index regenerates _index.md. | Aok | Should | 2 | 3 | 2 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3
US-36 | Quality | Integration day + bug bash + demo prep | Full happy-path + failure-path test on real Firebase project; seed demo data; record screencast. | All | Must | 2 | 5 | 8 | 5 | 5 | 8 |  |  |  |  | 5 | 5 | 5 | 8 | 5 |  |  |  |  | 5 | 5 | 5 | 5 | 5
TOTAL

## Summary by Epic
Epic | Items | Consensus SP total | Person-days est.
Identity
Catalog
Request
Fleet
Tracking
Backend
DevOps
Audit
Quality
TOTAL

## Summary by Owner
Owner | Items | Consensus SP | Person-days | Capacity (14d) | Utilization
Aok |  |  |  | 14
Belle |  |  |  | 14
Bew |  |  |  | 14
Poom |  |  |  | 14
Tawan |  |  |  | 14
All |  |  |  | 0