## Legend
DroneAid — GANTT chart legend
Project window: 2026-05-22 → 2026-06-04 (14 days, 7-day work week)
Owner color coding
Aok
Belle
Bew
Poom
Tawan
All
Sprints
Sprint 0 | Bootstrap (Days 1–2)
Sprint 1 | Auth + Catalog + Submit (Days 3–7)
Sprint 2 | Admin manage + Fleet + Tracking core (Days 7–9)
Sprint 3 | Simulator + Failures + Weather + Confirm (Days 9–12)
Sprint 4 | Notifications + Inventory + CI/CD (Days 11–12)
Sprint 5 | Integration + Demo (Days 13–14)

## GANTT
ID | Task | Owner | Sprint | Start | End | Dur | Depends on | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
| Date / DoW | [6 empty] | 05-22 Fri | 05-23 Sat | 05-24 Sun | 05-25 Mon | 05-26 Tue | 05-27 Wed | 05-28 Thu | 05-29 Fri | 05-30 Sat | 05-31 Sun | 06-01 Mon | 06-02 Tue | 06-03 Wed | 06-04 Thu
T-01 | Firebase project setup + emulator suite | Aok | S1 | 1 | 2 | 2 |  | D1: T-01; D2: T-01
T-02 | Flutter scaffold: theme, go_router, Riverpod, env | Belle | S1 | 1 | 2 | 2 |  | D1: T-02; D2: T-02
T-03 | Data model classes + repository stubs (all features) | Aok | S1 | 2 | 3 | 2 | T-01 | D2: T-03; D3: T-03
T-04 | Firestore rules v0 + indexes | Aok | S1 | 2 | 3 | 2 | T-01 | D2: T-04; D3: T-04
T-05 | Thai national-ID validator + unit tests | Belle | S1 | 2 | 3 | 2 |  | D2: T-05; D3: T-05
T-06 | Login + register pages | Belle | S1 | 3 | 4 | 2 | T-05, T-02 | D3: T-06; D4: T-06
T-07 | onUserCreated trigger | Aok | S1 | 3 | 3 | 1 | T-01, T-04 | D3: T-07
T-08 | Profile + Settings pages | Belle | S1 | 4 | 5 | 2 | T-06 | D4: T-08; D5: T-08
T-09 | Shared widgets: DroneMap, BatteryBar, StatusChip, ItemPicker | Belle | S1 | 5 | 7 | 3 | T-02 | D5: T-09; D6: T-09; D7: T-09
T-10 | Catalog browse + cart (user) | Bew | S1 | 4 | 5 | 2 | T-03 | D4: T-10; D5: T-10
T-11 | Pin picker on map | Bew | S1 | 5 | 6 | 2 | T-03, T-09 | D5: T-11; D6: T-11
T-12 | submitRequest callable + tests | Aok | S1 | 4 | 5 | 2 | T-03, T-04 | D4: T-12; D5: T-12
T-13 | Submit + Queue page (live stream) | Bew | S1 | 6 | 7 | 2 | T-10, T-11, T-12 | D6: T-13; D7: T-13
T-14 | Admin Requests list (read) | Bew | S1 | 6 | 7 | 2 | T-03 | D6: T-14; D7: T-14
T-15 | approveRequest + rejectRequest callables (stock tx) | Aok | S2 | 7 | 8 | 2 | T-12 | D7: T-15; D8: T-15
T-16 | Admin Request Manage page: approve/reject + drone picker | Bew | S2 | 7 | 9 | 3 | T-14, T-15 | D7: T-16; D8: T-16; D9: T-16
T-17 | Admin Drone list page | Tawan | S1 | 6 | 7 | 2 | T-03 | D6: T-17; D7: T-17
T-18 | Admin Drone detail page + future queue | Tawan | S2 | 7 | 9 | 3 | T-17 | D7: T-18; D8: T-18; D9: T-18
T-19 | Drone fleet seed data | Tawan | S2 | 8 | 8 | 1 | T-04 | D8: T-19
T-20 | assignDrone callable + flight document | Aok | S2 | 8 | 9 | 2 | T-15, T-19 | D8: T-20; D9: T-20
T-21 | Tracking page: flutter_map + interpolation math | Poom | S2 | 8 | 10 | 3 | T-09 | D8: T-21; D9: T-21; D10: T-21
T-22 | Admin Control live map | Poom | S2 | 9 | 11 | 3 | T-09, T-21 | D9: T-22; D10: T-22; D11: T-22
T-23 | tickFlights v0: movement + state transitions | Aok | S3 | 10 | 11 | 2 | T-20 | D10: T-23; D11: T-23
T-24 | Confirm page + confirmDelivery wiring | Poom | S3 | 10 | 11 | 2 | T-21 | D10: T-24; D11: T-24
T-25 | confirmDelivery callable | Aok | S3 | 11 | 11 | 1 | T-20 | D11: T-25
T-26 | tickFlights failures: weather + battery + mechanical | Aok | S3 | 11 | 12 | 2 | T-23 | D11: T-26; D12: T-26
T-27 | Admin Weather panel + setWeather callable | Tawan | S3 | 9 | 11 | 3 | T-04 | D9: T-27; D10: T-27; D11: T-27
T-28 | History page (user) | Bew | S3 | 10 | 11 | 2 | T-13 | D10: T-28; D11: T-28
T-29 | FCM device registration + token sync | Poom | S4 | 11 | 12 | 2 | T-06 | D11: T-29; D12: T-29
T-30 | Notifications inbox page | Poom | S4 | 12 | 12 | 1 | T-29 | D12: T-30
T-31 | onFlightWritten trigger + FCM fan-out | Aok | S4 | 12 | 12 | 1 | T-26, T-29 | D12: T-31
T-32 | Admin Inventory + restock callable + page | Bew | S4 | 11 | 12 | 2 | T-15 | D11: T-32; D12: T-32
T-33 | toggleDroneMaintenance + cancelRequest callables | Aok | S4 | 12 | 12 | 1 | T-20 | D12: T-33
T-34 | GitHub Actions: CI (flutter+functions+rules+gitleaks+logs) | Aok | S2 | 7 | 9 | 3 | T-04 | D7: T-34; D8: T-34; D9: T-34
T-35 | GitHub Actions: deploy workflows | Aok | S3 | 9 | 10 | 2 | T-34 | D9: T-35; D10: T-35
T-36 | SessionEnd hook + copy + redact-secrets scripts | Belle | S2 | 7 | 8 | 2 |  | D7: T-36; D8: T-36
T-37 | log-presence + build-log-index workflows | Aok | S3 | 10 | 11 | 2 | T-34, T-36 | D10: T-37; D11: T-37
T-38 | Integration testing on real Firebase project (full path) | All | S5 | 13 | 13 | 1 | T-31, T-32, T-33 | D13: T-38
T-39 | Bug bash + polish | All | S5 | 13 | 14 | 2 | T-38 | D13: T-39; D14: T-39
T-40 | Demo seed dataset + screenshots + screencast | All | S5 | 14 | 14 | 1 | T-39 | D14: T-40
T-41 | README + presentation slides | All | S5 | 14 | 14 | 1 | T-39 | D14: T-41
Milestones | bar: D5; D7; D9; D11 to D12; D14
[12 empty] | M1: Auth working |  | M2: Submit + admin manage skeleton |  | M3: Drone assignment + tracking |  | M4: Simulator + failures live | M5: Notifications + inventory |  | M6: Demo ready

## Daily swimlane
Owner / Day | D1 05-22 Fri | D2 05-23 Sat | D3 05-24 Sun | D4 05-25 Mon | D5 05-26 Tue | D6 05-27 Wed | D7 05-28 Thu | D8 05-29 Fri | D9 05-30 Sat | D10 05-31 Sun | D11 06-01 Mon | D12 06-02 Tue | D13 06-03 Wed | D14 06-04 Thu
Aok | T-01 | T-01 T-03 T-04 | T-03 T-04 T-07 | T-12 | T-12 |  | T-15 T-34 | T-15 T-20 T-34 | T-20 T-34 T-35 | T-23 T-35 T-37 | T-23 T-25 T-26 T-37 | T-26 T-31 T-33
Belle | T-02 | T-02 T-05 | T-05 T-06 | T-06 T-08 | T-08 T-09 | T-09 | T-09 T-36 | T-36
Bew |  |  |  | T-10 | T-10 T-11 | T-11 T-13 T-14 | T-13 T-14 T-16 | T-16 | T-16 | T-28 | T-28 T-32 | T-32
Poom | [7 empty] | T-21 | T-21 T-22 | T-21 T-22 T-24 | T-22 T-24 T-29 | T-29 T-30
Tawan | [5 empty] | T-17 | T-17 T-18 | T-18 T-19 | T-18 T-27 | T-27 | T-27
All | [12 empty] | T-38 T-39 | T-39 T-40 T-41

## Workload
Owner | Tasks | Person-days | Capacity (14d) | Utilization
Aok | 15 | 27 | 14
Belle | 6 | 13 | 14
Bew | 7 | 15 | 14
Poom | 5 | 11 | 14
Tawan | 4 | 9 | 14
All | 4 | 5 | 0